## Weight
Sky Pup / Airbike Derivative - Weight and Balance
130 sq ft 3-piece wood wing, welded 4130 fuselage, 2-axis + spoilerons, tricycle gear, Hirth F-33.
Datum = prop plane. Wing LE sta 48, chord 50 in. Blue=estimate, yellow=type measured, it overrides.
Column '103 Strip' is the weight of that item in the Part 103 configuration. 0 means deleted.
Item | Group | Est lb | Measured lb | Used lb | Station | Moment | 103 Strip lb
Spar: 1.25 sch40 caps, wrapped web, rivets | Wing | 22 |  | 22 | 72 | 1584 | 22
Ribs, 31 ea, Douglas fir truss | Wing | 8 |  | 8 | 74 | 592 | 8
D-tube leading edge, 1/16 birch ply | Wing | 12 |  | 12 | 60 | 720 | 12
Rear spar / spoileron hinge spar | Wing | 5 |  | 5 | 86 | 430 | 5
Trailing edge stock | Wing | 3 |  | 3 | 100 | 300 | 3
Joint rods, sleeves, 8 bolts | Wing | 7 |  | 7 | 68 | 476 | 7
Spoilerons, hinges, return springs | Wing | 4 |  | 4 | 82 | 328 | 4
Fabric and finish, 260 sq ft | Wing | 14 |  | 14 | 74 | 1036 | 11.5
Wing misc hardware | Wing | 4 |  | 4 | 72 | 288 | 4
4130 longerons, verticals, diagonals | Fuselage | 28 |  | 28 | 85 | 2380 | 28
Cluster gussets and brackets | Fuselage | 3 |  | 3 | 80 | 240 | 3
Structural nose bow | Fuselage | 4 |  | 4 | 30 | 120 | 4
Rollover hoop | Fuselage | 4 |  | 4 | 54 | 216 | 4
Seat structure and Confor foam | Fuselage | 6 |  | 6 | 58 | 348 | 6
5-point harness | Fuselage | 4 |  | 4 | 58 | 232 | 4
Turtledeck formers | Fuselage | 3 |  | 3 | 110 | 330 | 3
Fuselage fabric and finish, 100 sq ft | Fuselage | 6 |  | 6 | 85 | 510 | 5
Windshield | Fuselage | 4 |  | 4 | 42 | 168 | 0
Horizontal stab and elevator, 30 sq ft | Tail | 12 |  | 12 | 184 | 2208 | 11
Vertical fin and rudder, 15 sq ft | Tail | 6 |  | 6 | 180 | 1080 | 5.5
Tail attach fittings | Tail | 2 |  | 2 | 182 | 364 | 2
Sprung 4130 main gear legs | Gear | 8 |  | 8 | 80 | 640 | 7
Main wheels and tires | Gear | 12 |  | 12 | 80 | 960 | 8
Bicycle hydraulic brakes and adapters | Gear | 3 |  | 3 | 80 | 240 | 3
Nose gear leg, wheel, steering | Gear | 12 |  | 12 | 36 | 432 | 9
Gear mounts and fittings | Gear | 3 |  | 3 | 60 | 180 | 3
Stick, elevator run, bellcranks | Controls | 7 |  | 7 | 60 | 420 | 7
Rudder pedals and cables | Controls | 5 |  | 5 | 100 | 500 | 5
Spoileron cables, pulleys, springs | Controls | 4 |  | 4 | 74 | 296 | 4
Hirth F-33, 28 hp, incl exhaust | Power | 35 |  | 35 | 14 | 490 | 28
Belt reduction drive | Power | 10 |  | 10 | 10 | 100 | 0
Propeller, wood, 60 in | Power | 8 |  | 8 | 2 | 16 | 7
Engine mount | Power | 5 |  | 5 | 18 | 90 | 4
Fuel tank, lines, shutoff | Power | 8 |  | 8 | 50 | 400 | 5
Junco, tablet, mount | Systems | 4 |  | 4 | 44 | 176 | 0
Wiring, switches, master | Systems | 2 |  | 2 | 50 | 100 | 0
BRS hard points and bridle channel | Systems | 3 |  | 3 | 70 | 210 | 3
AN hardware, paint, placards | Systems | 6 |  | 6 | 80 | 480 | 5
EMPTY WEIGHT |  |  |  | 296 | 66.4865 | 19680 | 250
Empty CG is in the Station column. Part 103 limit is 254 lb.
BY GROUP
Group | lb | % of empty | 103 lb
Wing | 79 | 26.69% | 76.5
Fuselage | 62 | 20.95% | 57
Tail | 20 | 6.757% | 18.5
Gear | 38 | 12.84% | 30
Controls | 16 | 5.405% | 16
Power | 66 | 22.3% | 44
Systems | 15 | 5.068% | 8
LOADED CG CASES
Pilot station | 58
Fuel station | 50
Wing LE station | 48 | Target CG 25-35% MAC. Move this to trim the CG.
Case | Pilot lb | Fuel lb | Gross lb | CG in | % MAC
Allen, full fuel | 170 | 30 | 496 | 62.5806 | 29.16%
Allen, no fuel | 170 | 0 | 466 | 63.3906 | 30.78%
220 lb pilot | 220 | 30 | 546 | 62.1612 | 28.32%
130 lb pilot | 130 | 30 | 456 | 62.9825 | 29.96%

## Cost
Bill of Materials
OnlineMetals for 6061 and 4130, lumber yard for select vertical grain Douglas fir.
Item | Category | Est $ | Actual $ | Used $ | Note
1.25 sch40 6061-T6 spar caps, 62 ft | Wing | 650 |  | 650 | Verify 6061-T6, not 6063
0.020 6061 web sheet plus rivets | Wing | 200 |  | 200
Douglas fir, truss ribs and wing structure | Wing | 200 |  | 200 | Lumber yard, VG, 6+ rings/in
1/16 birch ply, D-tube | Wing | 180 |  | 180
Rear spar tube and trailing edge | Wing | 150 |  | 150
Joint rods, sleeves, AN bolts | Wing | 220 |  | 220 | Machine shop stock
Spoileron hinges, springs, cable | Wing | 180 |  | 180
4130 tube, fuselage | Fuselage | 500 |  | 500
4130 tube, tail surfaces | Fuselage | 200 |  | 200
Welding gas and filler | Fuselage | 100 |  | 100
Windshield polycarbonate | Fuselage | 150 |  | 150
Seat, Confor foam, 5-point harness | Fuselage | 350 |  | 350
Stewart Systems fabric and finish, 430 sq ft | Covering | 1400 |  | 1400 | Waterborne
Hirth F-33 with belt redrive | Power | 4200 |  | 4200 | Used runs ~2500. See options below
Propeller, wood, 60 in | Power | 350 |  | 350
Fuel tank, lines, shutoff, filter | Power | 200 |  | 200
Main wheels and tires, no brakes | Gear | 250 |  | 250
Bicycle hydraulic disc brakes x2 | Gear | 250 |  | 250 | DH grade, 203mm rotors
Rotor-to-hub adapters, material | Gear | 50 |  | 50 | Machine yourself
Nose gear, wheel, steering linkage | Gear | 400 |  | 400
4130 sprung gear leg stock | Gear | 120 |  | 120
Cables, pulleys, rod ends, stick, pedals | Controls | 500 |  | 500
AN hardware, bolts, nuts, washers | Hardware | 500 |  | 500 | Always underestimated
Junco, tablet, mount | Systems | 350 |  | 350
BRS hard points and doublers | Systems | 60 |  | 60 | No chute installed
Epoxy, glue, abrasives, consumables | Consumables | 350 |  | 350
Weld jig, wing jig, misc tooling | Tooling | 200 |  | 200
DAR inspection and N-number | Cert | 755 |  | 755
MATERIALS SUBTOTAL |  |  |  | 13015
Contingency |  | 30% |  | 3904.5
TOTAL |  |  |  | 16919.5
ENGINE OPTIONS - the only line that decides the $15k target
Option | Engine $ | Total $ | Weight lb | Ignition
Hirth F-33, new | 4200 | 16919.5 | 45 | Dual CDI
Hirth F-33, used | 2500 | 14709.5 | 45 | Dual CDI
Rotax 277, used | 1200 | 13019.5 | 62 | Single

## Hours
Build Hours
Design time excluded. Sky Pup baseline is 450-600 hr. Your experience factor is applied below.
Task | Phase | Raw hr | Actual hr | Used hr | Note
Weld jig and fuselage structure | Fuselage | 130 |  | 130 | Your MIG/TIG work
Nose bow, rollover hoop, seat frame | Fuselage | 40 |  | 40
Tail surfaces, weld and assemble | Tail | 55 |  | 55
Spar: cut, drill, rivet, both panels + center | Wing | 90 |  | 90
Cut and jig 31 fir truss ribs | Wing | 45 |  | 45 | 75 min each
D-tube leading edge | Wing | 45 |  | 45
Wing assembly, TE, tips, dihedral set | Wing | 50 |  | 50
Spoilerons, hinges, springs | Wing | 30 |  | 30 | You have done these
Wing joint fittings and fit-up | Wing | 35 |  | 35 | Machine shop
Sprung main gear, nose gear, steering | Gear | 50 |  | 50
Brake install, rotor adapters, bleed | Gear | 20 |  | 20
Elevator and rudder runs | Controls | 40 |  | 40
Spoileron cables, pulleys, rigging | Controls | 25 |  | 25
Engine mount, install, fuel, exhaust | Power | 55 |  | 55
Cover and finish, 430 sq ft | Finish | 120 |  | 120 | Slowest single task
Final assembly, rigging, weigh, debug | Assembly | 75 |  | 75
Remakes and learning curve | Contingency | 85 |  | 85
RAW TOTAL |  |  |  | 990
Experience factor |  | 70% |  |  | Your estimate of my estimates
ADJUSTED TOTAL HOURS |  |  |  | 693
Hours per week |  | 12
Calendar years |  | 1.1106

## Performance
Performance, driven live off the Weight sheet
INPUTS
Wing span (ft) | 31 | 3-piece: 8 ft center, 11.5 ft outer panels
Wing area (sq ft) | 130 | Constant chord 50 in
Equiv flat plate area f (sq m) | 0.45 | Back-solved from Sky Pup 12:1, plus trike gear
Oswald efficiency e | 0.85
CLmax, clean | 1.4 | Sky Pup section, no flaps
Engine shaft hp | 28 | Hirth F-33
Prop efficiency, cruise | 0.75 | 60 in wood, fixed pitch
Prop efficiency, climb | 0.72
Static thrust (lb) | 211 | 28 hp on a 60 in disc, FM 0.75
Roll friction + drag coeff | 0.1 | Grass
Cruise speed (mph) | 50
Fuel burn at cruise (gph) | 1.4 | 2-stroke, part throttle
Fuel capacity (gal) | 5
Design pilot (lb) | 170
Fuel aboard (lb) | 30
DERIVED
Gross weight (lb) | 496
Gross weight (N) | 2206.3171
Span (m) | 9.4488
Wing area (sq m) | 12.0774
L/D max | 11.5087 | Sky Pup is 12:1
Stall speed (mph) | 32.6501 | Part 103 limit 27.6 mph
Liftoff speed (m/s) | 16.7853
Takeoff accel (m/s2) | 2.5662
GROUND ROLL (ft) | 180.1013 | Target under 200 ft
Cruise speed (m/s) | 22.352
Parasite power at cruise (W) | 3077.9787
Induced power at cruise (W) | 1491.3926
Shaft hp required at cruise | 8.1702
Best climb speed (m/s) | 19.3031
Power required at Vy (W) | 3709.3822
RATE OF CLIMB (fpm) | 1010.3333
ENDURANCE (hours) | 3.5714
RANGE (statute miles) | 178.5714 | Less reserve
Wing loading (lb/sq ft) | 3.8154
Power loading (lb/hp) | 17.7143
Glide distance from 1000 ft AGL (mi) | 2.1797
Max achievable g = (Vne/Vstall)^2. Design limit 4.7g, ultimate 7.0g makes the wing stall-limited.